# ProjectPulse — Client Communication & Escalation Log

This log records all formal client communications, escalations, and decisions across active projects. Used by Delivery Heads to track relationship health.

## KT-003 | RetailMax Europe — CRITICAL ESCALATION

| Date | Type | Participants | Summary | Outcome |
| --- | --- | --- | --- | --- |
| Mar 20 2025 | Emergency Call | James Turner, Client CTO, Delivery Head | Go-live missed. Client furious. Demanding recovery plan. | Recovery plan due Mar 22 |
| Mar 22 2025 | Recovery Plan Submitted | James Turner → Client PMO | Submitted revised go-live plan targeting May 15 2025 | Client reviewing — response pending |
| Apr 1 2025 | Escalation Email | Client CEO → Kaartech CEO | Formal escalation. Mention of contract penalty clause review. | Kaartech CEO notified. Legal reviewing. |
| Apr 10 2025 | Steering Committee | Kaartech Delivery Head, Client CEO, CFO | Agreed recovery plan with new go-live: Jun 30 2025. Penalty clause suspended. | Client cautiously agrees. Weekly updates required. |
| Apr 25 2025 | Weekly Status Call | James Turner, Client PMO | Progress reviewed. 3 open items from recovery plan completed. | Client satisfaction: 5/10. Improving. |
| May 2 2025 | Weekly Status Call | James Turner, Client PMO | Config complete. Integration testing 80% done. | Client satisfaction: 6/10. |

## KT-010 | Metro Power Grid — HIGH URGENCY

| Date | Type | Participants | Summary | Outcome |
| --- | --- | --- | --- | --- |
| Apr 5 2025 | Status Call | David Clarke, Client IT Director | UAT environment setup delayed by client infra team. | Client IT Director to resolve by Apr 15. |
| Apr 16 2025 | Escalation Call | David Clarke, Client IT Director, VP Delivery | UAT environment still not ready. Go-live risk raised formally. | Client escalated internally to their CTO. |
| Apr 22 2025 | Emergency Meeting | VP Delivery, Client CTO | UAT environment promised by Apr 30. Regulatory deadline discussed. | Agreed: if UAT not started by May 5, go-live postponed to Sep 2025. |
| May 1 2025 | Status Update | David Clarke, Client IT Director | UAT environment partially ready. Testing not yet started. | Critical: decision point approaching May 5. |

## KT-001 | Acme Manufacturing — MEDIUM ESCALATION

| Date | Type | Participants | Summary | Outcome |
| --- | --- | --- | --- | --- |
| Apr 1 2025 | Status Call | Ravi Kumar, Client Project Manager | UAT sign-off delayed — key approver unavailable. | Client to name backup approver by Apr 10. |
| Apr 10 2025 | Follow-up Email | Ravi Kumar → Client PM | No backup approver named. Reminder sent. | No response received. |
| Apr 22 2025 | Escalation Call | Ravi Kumar, Account Manager, Client Director | Formal request for UAT sign-off resolution. | Client Director intervening. New meeting scheduled May 5. |
| May 5 2025 | UAT Meeting | Ravi Kumar, Client Director, Business Team | UAT walk-through completed. 12 minor defects raised. | Defects to be resolved by May 12. Sign-off targeted May 15. |

## Overall Client Satisfaction Scores (May 2025)

| Project | Client | Satisfaction Score | Trend | Last Survey Date |
| --- | --- | --- | --- | --- |
| KT-001 | Acme Manufacturing | 6/10 | 🟡 Stable | May 1 2025 |
| KT-002 | Gulf Energy Co | 9/10 | ✅ Improving | Apr 25 2025 |
| KT-003 | RetailMax Europe | 5/10 | 🟡 Recovering (was 3/10) | May 2 2025 |
| KT-004 | BioLife Pharma | 7/10 | ✅ Stable | Apr 28 2025 |
| KT-005 | Sunrise Steel | 10/10 | ✅ Excellent | May 1 2025 |
| KT-006 | NovaTech Logistics | 6/10 | 🔴 Declining | Apr 20 2025 |
| KT-009 | Alpine Insurance | 9/10 | ✅ Excellent | Apr 30 2025 |
| KT-010 | Metro Power Grid | 4/10 | 🔴 Critical | May 1 2025 |
| KT-014 | Gulf Retail Chain | 8/10 | ✅ Good | Apr 28 2025 |
| KT-015 | SkyWings Airlines | 6/10 | 🔴 Declining — resource issue | May 2 2025 |