# ProjectPulse — KPI Dashboard & Delivery Performance Report

Monthly KPI report for May 2025. Covers all 15 SAP projects across 4 regions. Used by Delivery Head for board-level reporting.

## Portfolio KPI Summary — May 2025

| KPI | Target | Actual | Status |
| --- | --- | --- | --- |
| Projects delivered on time (YTD) | > 85% | 72% (13/15 on track) | 🟡 Below Target |
| Projects within budget | > 90% | 73% (11/15) | 🔴 Below Target |
| Client satisfaction average | > 8/10 | 6.9/10 | 🟡 Below Target |
| Critical risks resolved within SLA | 100% in 24hrs | 80% | 🟡 Needs Improvement |
| Go-live success rate (2025) | > 90% | 50% (1 of 2 scheduled) | 🔴 Critical |
| Resource utilisation rate | 85-90% | 88% | ✅ On Target |
| Change request turnaround | < 5 days | 7.2 days average | 🟡 Slightly Over |
| Post go-live defects (P1) | < 3 per project | 1.5 average | ✅ On Target |

## On-Time Delivery Performance by Region

| Region | Active Projects | On Track | At Risk | Critical | On-Time Rate |
| --- | --- | --- | --- | --- | --- |
| APAC | 5 | 3 | 1 (KT-001) | 1 (KT-015) | 60% |
| Europe | 3 | 1 (KT-009) | 1 (KT-006) | 1 (KT-003) | 33% |
| Middle East | 3 | 2 | 1 (KT-007 on hold) | 0 | 67% |
| North America | 3 | 1 (KT-004) | 0 | 2 (KT-010, KT-012) | 33% |

## SAP Module Performance — Risk Analysis

| SAP Module | Active Projects | Average Budget Burn | Avg Risk Level | Key Issue |
| --- | --- | --- | --- | --- |
| SAP S/4HANA | 6 | 64% | MEDIUM | Complex transformations causing UAT delays |
| SAP Ariba | 2 | 84% | HIGH | Both projects facing delivery challenges |
| SAP ECC | 1 | 45% | LOW | Stable — maintenance project |
| SAP SuccessFactors | 1 | 62% | MEDIUM | Data migration and GDPR compliance |
| SAP TM | 1 | 88% | HIGH | Scope creep — budget at risk |
| SAP PM | 1 | 91% | CRITICAL | UAT not started — go-live at risk |
| SAP EWM | 1 | 66% | MEDIUM | Config freeze needed |
| SAP PP | 1 | 50% | LOW | Small project — stable |

## Top 5 Delivery Recommendations for Delivery Head

1. IMMEDIATE: Resolve KT-010 Metro Power Grid go-live decision

- Decision point: May 5 2025 — is UAT starting or is go-live postponed to September?

- Financial impact of postponement: $50,000+ in extended engagement costs

2. URGENT: Assign FICO replacement to KT-015 SkyWings Airlines

- Every week of delay costs the project 3 weeks of catch-up effort

- Arjun V. on bench — approve deployment immediately

3. COMMERCIAL: Formalise KT-003 and KT-006 change requests

- Combined uncaptured revenue: $90,000+

- Commercial discussions must be led by Account Manager this week

4. QUALITY: Improve average client satisfaction from 6.9 to 8.0 by July

- Focus on KT-003, KT-006, KT-010 — these three drag the average down

- Weekly Delivery Head touchpoints with these three clients

5. PROCESS: Enforce change control across all projects

- Scope creep is the leading cause of budget overruns in this portfolio

- Mandatory change request process to be re-communicated to all PMs this week