# ProjectPulse — Milestone Tracker

This document tracks key delivery milestones for all active SAP projects. Milestones are categorised as: Completed ✅, On Track 🟡, Delayed 🔴.

## KT-001 | Acme Manufacturing | SAP S/4HANA

| Milestone | Planned Date | Actual/Forecast | Status | Owner |
| --- | --- | --- | --- | --- |
| Project Kickoff | Jan 15 2024 | Jan 15 2024 | ✅ Done | Ravi Kumar |
| Blueprint Sign-off | Mar 1 2024 | Mar 8 2024 | ✅ Done | Ravi Kumar |
| System Build Complete | Jun 1 2024 | Jun 14 2024 | ✅ Done | Ravi Kumar |
| Integration Testing | Sep 1 2024 | Oct 1 2024 | ✅ Done | Ravi Kumar |
| UAT Start | Jan 15 2025 | Jan 15 2025 | ✅ Done | Ravi Kumar |
| UAT Sign-off | Mar 15 2025 | PENDING - 3 weeks blocked | 🔴 Delayed | Ravi Kumar |
| Go-Live Prep | Apr 1 2025 | TBD | 🔴 Blocked | Ravi Kumar |
| Go-Live | Jun 1 2025 | TBD | 🔴 At Risk | Ravi Kumar |

## KT-003 | RetailMax Europe | SAP Ariba

| Milestone | Planned Date | Actual/Forecast | Status | Owner |
| --- | --- | --- | --- | --- |
| Project Kickoff | Nov 15 2023 | Nov 15 2023 | ✅ Done | James Turner |
| Blueprint Sign-off | Jan 20 2024 | Feb 5 2024 | ✅ Done | James Turner |
| System Build Complete | Jun 1 2024 | Jul 15 2024 | ✅ Done | James Turner |
| Integration Testing | Sep 15 2024 | Nov 1 2024 | ✅ Done | James Turner |
| UAT Sign-off | Jan 31 2025 | Feb 28 2025 | ✅ Done | James Turner |
| Go-Live | Mar 15 2025 | NOT YET LIVE | 🔴 CRITICAL | James Turner |
| Post Go-Live Support | Apr 1 2025 | Not Started | 🔴 BLOCKED | James Turner |

## KT-010 | Metro Power Grid | SAP PM

| Milestone | Planned Date | Actual/Forecast | Status | Owner |
| --- | --- | --- | --- | --- |
| Project Kickoff | Oct 10 2023 | Oct 10 2023 | ✅ Done | David Clarke |
| Blueprint Sign-off | Dec 20 2023 | Jan 15 2024 | ✅ Done | David Clarke |
| System Build Complete | May 1 2024 | May 20 2024 | ✅ Done | David Clarke |
| Integration Testing | Aug 1 2024 | Sep 1 2024 | ✅ Done | David Clarke |
| UAT Start | Feb 1 2025 | NOT STARTED | 🔴 CRITICAL | David Clarke |
| UAT Sign-off | Apr 15 2025 | NOT STARTED | 🔴 CRITICAL | David Clarke |
| Go-Live | Jun 1 2025 | UNLIKELY | 🔴 CRITICAL | David Clarke |

## KT-005 | Sunrise Steel | SAP S/4HANA

| Milestone | Planned Date | Actual/Forecast | Status | Owner |
| --- | --- | --- | --- | --- |
| Project Kickoff | Apr 10 2024 | Apr 10 2024 | ✅ Done | Karthik M |
| Blueprint Sign-off | Jun 15 2024 | Jun 15 2024 | ✅ Done | Karthik M |
| System Build Complete | Oct 1 2024 | Oct 5 2024 | ✅ Done | Karthik M |
| Integration Testing | Jan 15 2025 | Jan 20 2025 | ✅ Done | Karthik M |
| UAT Start | Mar 1 2025 | Mar 1 2025 | ✅ Done | Karthik M |
| UAT Sign-off | May 15 2025 | May 18 2025 (forecast) | 🟡 On Track | Karthik M |
| Go-Live | Nov 1 2025 | Nov 1 2025 (on track) | 🟡 On Track | Karthik M |