## SAP Projects
Project ID | Client Name | Industry | SAP Module | Region | Status | Budget (USD) | Spent % | Start Date | Go-Live Date | PM Name | Team Size | Risk Level | Notes
KT-2024-001 | Acme Manufacturing | Manufacturing | SAP S/4HANA | APAC | Active | 500000 | 78 | Jan 2024 | Jun 2025 | Ravi Kumar | 12 | HIGH | UAT sign-off pending from client for 3 weeks
KT-2024-002 | Gulf Energy Co | Energy | SAP ECC | Middle East | Active | 300000 | 45 | Mar 2024 | Aug 2025 | Priya Sharma | 8 | LOW | On track, client very responsive
KT-2024-003 | RetailMax Europe | Retail | SAP Ariba | Europe | Delayed | 750000 | 97 | Nov 2023 | Mar 2025 | James Turner | 15 | CRITICAL | Go-live passed, client escalated to leadership
KT-2024-004 | BioLife Pharma | Healthcare | SAP SuccessFactors | North America | Active | 420000 | 62 | Feb 2024 | Sep 2025 | Anitha Raj | 10 | MEDIUM | HR data migration 2 weeks behind schedule
KT-2024-005 | Sunrise Steel | Manufacturing | SAP S/4HANA | APAC | Active | 680000 | 55 | Apr 2024 | Nov 2025 | Karthik M | 14 | LOW | Excellent client collaboration, all milestones met
KT-2024-006 | NovaTech Logistics | Logistics | SAP TM | Europe | Active | 310000 | 88 | Dec 2023 | Apr 2025 | Marco Rossi | 9 | HIGH | Budget nearly exhausted, scope creep identified
KT-2024-007 | Desert Palm Hotels | Hospitality | SAP S/4HANA | Middle East | On Hold | 250000 | 40 | Jan 2024 | Oct 2025 | Fatima Al-Zahra | 7 | MEDIUM | Client paused project for internal restructuring
KT-2024-008 | Pacific Foods | Consumer Goods | SAP Ariba | APAC | Active | 390000 | 70 | Feb 2024 | Jul 2025 | Chen Wei | 11 | MEDIUM | Integration testing delayed by 1 week
KT-2024-009 | Alpine Insurance | BFSI | SAP S/4HANA | Europe | Active | 820000 | 35 | May 2024 | Jan 2026 | Sophie Müller | 18 | LOW | Large programme, well governed, green status
KT-2024-010 | Metro Power Grid | Utilities | SAP PM | North America | Active | 560000 | 91 | Oct 2023 | May 2025 | David Clarke | 13 | CRITICAL | Go-live in 4 weeks, UAT not started
KT-2024-011 | Indus Textiles | Manufacturing | SAP PP | APAC | Active | 190000 | 50 | Jun 2024 | Dec 2025 | Suresh Babu | 6 | LOW | Small project, progressing smoothly
KT-2024-012 | Atlantic Shipping | Logistics | SAP EWM | North America | Active | 470000 | 66 | Jan 2024 | Aug 2025 | Maria Gonzalez | 10 | MEDIUM | Warehouse configuration 10 days behind plan
KT-2024-013 | Nordic Pharma | Healthcare | SAP QM | Europe | Completed | 280000 | 100 | Jun 2023 | Jan 2025 | Erik Lindqvist | 8 | LOW | Successfully delivered, client very satisfied
KT-2024-014 | Gulf Retail Chain | Retail | SAP S/4HANA | Middle East | Active | 610000 | 48 | Mar 2024 | Oct 2025 | Omar Hassan | 13 | LOW | Mid-project, all systems green
KT-2024-015 | SkyWings Airlines | Aviation | SAP S/4HANA | APAC | Active | 900000 | 82 | Sep 2023 | Jun 2025 | Nisha Patel | 20 | HIGH | Key consultant resigned, replacement being arranged