# ProjectPulse — Resource Allocation & Skills Matrix

Total active consultants across portfolio: 168. This document tracks team allocation, key skills, and resource risks across all projects.

## Resource Allocation by Project

| Project | Client | PM | Team Size | Key Skills Required | Resource Risk |
| --- | --- | --- | --- | --- | --- |
| KT-001 | Acme Mfg | Ravi Kumar | 12 | SAP S/4HANA, FICO, MM, PP | 🟡 UAT lead unavailable |
| KT-002 | Gulf Energy | Priya Sharma | 8 | SAP ECC, FICO, SD | ✅ Fully staffed |
| KT-003 | RetailMax | James Turner | 15 | SAP Ariba, SRM, MDG | 🔴 Team morale low |
| KT-004 | BioLife Pharma | Anitha Raj | 10 | SuccessFactors, EC, Payroll | 🟡 2 data analysts needed |
| KT-005 | Sunrise Steel | Karthik M | 14 | SAP S/4HANA, PP, QM, PM | ✅ Fully staffed |
| KT-006 | NovaTech | Marco Rossi | 9 | SAP TM, EWM, SD | 🟡 Overloaded — scope creep |
| KT-007 | Desert Palm | Fatima Al-Zahra | 7 | SAP S/4HANA, FI, RE-FX | ⚫ Partially demobilised |
| KT-008 | Pacific Foods | Chen Wei | 11 | SAP Ariba, MM, integration | 🟡 Integration specialist busy |
| KT-009 | Alpine Insurance | Sophie Müller | 18 | SAP S/4HANA, FSRI, FICO | ✅ Well resourced |
| KT-010 | Metro Power | David Clarke | 13 | SAP PM, CS, FICO | 🔴 UAT team not mobilised |
| KT-011 | Indus Textiles | Suresh Babu | 6 | SAP PP, QM | ✅ Small team, stable |
| KT-012 | Atlantic Shipping | Maria Gonzalez | 10 | SAP EWM, TM, MM | 🟡 Config freeze pending |
| KT-013 | Nordic Pharma | Erik Lindqvist | 8 | SAP QM, GTS | ⚫ Project closed |
| KT-014 | Gulf Retail | Omar Hassan | 13 | SAP S/4HANA, SD, MM, FICO | ✅ Stable and on track |
| KT-015 | SkyWings | Nisha Patel | 20 | SAP S/4HANA, FICO, CO, PS | 🔴 FICO lead resigned |

## Critical Resource Risks

CRITICAL — KT-015 SkyWings Airlines: SAP FICO Lead Resigned

- Consultant name: Vikram S. (8 years SAP FICO experience)

- Left abruptly — sole owner of financial closing config and month-end automation

- Knowledge transfer only 30% complete at time of resignation

- Critical path blocked: financial period-end close, asset accounting, profit centre config

- Action: Search bench for FICO consultant with S/4 Finance experience minimum 5 years

- Action: Recovery plan — extract config from system, reverse-engineer from transport logs

HIGH — KT-001 Acme Manufacturing: UAT Lead Dependency

- Client's UAT lead is the sole business approver for sign-off

- Currently unavailable due to internal restructuring — no backup approver named

- Action: Request client to name an alternate approver within 5 business days

HIGH — KT-003 RetailMax Europe: Team Morale & Burnout Risk

- Team of 15 has been on project for 18 months — original timeline was 12 months

- 3 consultants have informally requested rotation to other projects

- Action: Delivery Head to conduct team welfare check. Rotate 2 consultants if project extends beyond Jun 2025

## Bench Resources Available for Deployment

| Name | Primary Skill | Secondary Skill | Available From | Suitable For |
| --- | --- | --- | --- | --- |
| Arjun V. | SAP FICO S/4HANA | CO, Profit Centre | Immediately | KT-015 SkyWings — CRITICAL |
| Deepa R. | SAP SuccessFactors | Employee Central | May 15 2025 | KT-004 BioLife — Data Migration |
| Liu W. | SAP Integration/PI | BTP, API Management | May 20 2025 | KT-008 Pacific Foods — API Fix |
| Hassan M. | SAP EWM | TM, MM | June 1 2025 | KT-012 Atlantic Shipping |
| Sara K. | SAP Ariba SRM | MDG, Procurement | Immediately | KT-003 RetailMax — Support |