# ProjectPulse — Project Health Rules & SOP

Standard Operating Procedure for SAP Project Health Monitoring

# 1. Project Health Status Definitions

GREEN — On Track: Budget spent is below 75% of total with timeline on schedule. All milestones delivered as planned. No unresolved HIGH or CRITICAL risks. Client satisfaction confirmed. No escalations active.

AMBER — At Risk: Any ONE of the following: Budget spent exceeds 85% with more than 20% of timeline remaining. Go-live date is within 30 days and UAT has not commenced. One or more HIGH severity risks unresolved for more than 7 days. One milestone delayed by more than 5 business days. Client has raised informal concerns.

RED — Critical: Any ONE of the following: Budget spent exceeds 95%. Go-live date has already passed and project is not live. A CRITICAL severity risk is unresolved for more than 3 days. Client has formally escalated to senior leadership. Delivery Head has been notified and is actively involved.

GREY — On Hold / Completed: Project has been formally paused by client decision or has been successfully delivered and closed.

# 2. Risk Severity Classification

CRITICAL: Immediate threat to project delivery, client relationship, or contractual compliance. Requires Delivery Head involvement within 24 hours. Daily status update mandatory.

HIGH: Significant risk with potential go-live impact of more than 2 weeks or budget overrun of more than 10%. Requires PM escalation within 48 hours. Bi-daily update required.

MEDIUM: Moderate risk being actively managed. Potential go-live delay of 1–2 weeks. Weekly status update required. PM to manage with team.

LOW: Minor risk with no current impact on schedule or budget. Logged and monitored. Fortnightly review sufficient.

# 3. Escalation Protocol

Level 1 — PM Action: All MEDIUM and LOW risks. PM resolves independently with team. No escalation needed unless risk severity increases.

Level 2 — Account Manager: HIGH risks persisting beyond 5 business days. Budget overrun risk above 10%. Client dissatisfaction expressed.

Level 3 — Delivery Head: CRITICAL risks at any time. RED project status. Client escalation to client senior leadership. Go-live date breach.

Level 4 — CEO / Board: Contract termination threat. Legal dispute initiated. Multiple simultaneous CRITICAL projects in same account.

# 4. Morning Briefing Rules

Briefing Schedule: Automated morning briefing sent daily at 08:00 AM local time of the Project Manager.

Briefing Content: Each PM receives only their own projects. Projects in GREEN status are summarised in one line. AMBER and RED projects receive full risk detail and recommended actions.

Delivery Head Summary: Delivery Head receives consolidated summary of all CRITICAL and RED projects across all regions. Sent at 08:30 AM IST daily.

Escalation Trigger: If any project changes from AMBER to RED status, an immediate Teams alert is sent to the Delivery Head and Account Manager — not waiting for next morning briefing.

# 5. Report Generation Standards

Client Status Report: Generated every Friday. Includes: Project overview, milestone status, risks log (HIGH and above), budget utilisation, next week's planned activities. Tone: professional, concise, client-friendly. No internal commentary.

Internal Delivery Report: Generated every Monday. Includes: Full risk register, resource utilisation, financial burn rate, escalation log, action items with owners and due dates.

On-Demand Reports: PM or Delivery Head can request a health report at any time by asking the agent. Report generated within 60 seconds using latest SharePoint data.

# 6. Key Performance Thresholds

Budget Alert 1: Triggered when project budget utilisation crosses 75%. Notification sent to PM only.

Budget Alert 2: Triggered when project budget utilisation crosses 85%. Notification sent to PM and Account Manager.

Budget Alert 3: Triggered when project budget utilisation crosses 95%. Notification sent to PM, Account Manager, and Delivery Head. Project status automatically set to RED.

Go-Live Warning: Triggered when go-live date is 30 days away and UAT completion is below 50%. AMBER status automatically assigned.

Go-Live Critical: Triggered when go-live date is 14 days away and UAT completion is below 80%. RED status automatically assigned and Delivery Head alerted.